## Product Backlog
Backlog ID | Epic | Feature | Description | Priority | Story Points | Status
PB-001 | Authentication | User Registration | Allow new users to create an account using email or mobile number. | High | 5 | To Do
PB-002 | Authentication | User Login | Allow registered users to log in securely. | High | 3 | To Do
PB-003 | Authentication | Forgot Password | Allow users to reset their password using OTP verification. | Medium | 3 | To Do
PB-004 | Dashboard | Financial Dashboard | Display income, expenses, savings, and budget overview. | High | 8 | To Do
PB-005 | Expense Management | Add Daily Expense | Allow users to record daily expenses manually. | High | 5 | To Do
PB-006 | Expense Management | Expense History | Display expense history with category-wise filtering. | Medium | 5 | To Do
PB-007 | Budget Planning | Monthly Budget Planner | Allow users to create and manage monthly budgets. | High | 8 | To Do
PB-008 | Financial Goals | Goal Management | Allow users to create and track financial goals based on subscription limits. | High | 8 | To Do
PB-009 | AI Insights | AI Financial Analysis | Generate AI-powered spending analysis and financial recommendations. | High | 13 | To Do
PB-010 | Financial Calculators | Financial Calculators | Provide calculators such as EMI, SIP, Compound Interest, and Budget Calculator. | Medium | 5 | To Do
PB-011 | Advisor Consultation | Advisor Matching | Match users with suitable financial advisors based on their financial concerns. | High | 8 | To Do
PB-012 | Advisor Consultation | Consultation Booking | Allow users to schedule and pay for online consultations. | High | 8 | To Do
PB-013 | Advisor Consultation | Video Consultation | Enable secure online video consultations between users and advisors. | High | 13 | To Do
PB-014 | Subscription | Subscription Management | Allow users to upgrade, downgrade, and manage subscription plans. | High | 5 | To Do
PB-015 | Notifications | Notifications & Reminders | Send reminders for expenses, budgets, goals, subscriptions, and consultations. | Medium | 5 | To Do

## User Stories
Story ID | Epic | User Story | Acceptance Criteria | Priority
US-001 | Authentication | As a new user, I want to register an account so that I can access personalized financial features. | 1. User can register using email or mobile number.2. Required fields must be validated.3. Account is created successfully after verification. | High
US-002 | Authentication | As a registered user, I want to log in securely so that I can access my financial dashboard. | 1. Valid credentials allow login.2. Invalid credentials display an error message.3. User is redirected to the dashboard after login. | High
US-003 | Dashboard | As a user, I want to view my financial summary so that I can quickly understand my financial status. | 1. Dashboard displays income, expenses, savings, and remaining budget.2. Data reflects the latest updates. | High
US-004 | Expense Management | As a user, I want to add my daily expenses so that I can track my spending habits. | 1. User can enter amount, category, and date.2. Expense is saved successfully.3. Dashboard updates automatically. | High
US-005 | Budget Planning | As a user, I want to create a monthly budget so that I can control my spending. | 1. User can define a monthly budget.2. Budget is saved successfully.3. Budget progress is displayed on the dashboard. | High
US-006 | Financial Goals | As a user, I want to create financial goals so that I can monitor my savings progress. | 1. User can create a goal with target amount and date.2. Goal progress is displayed.3. Goal limit follows the subscription plan. | High
US-007 | AI Insights | As a user, I want AI-generated financial insights so that I can improve my financial decisions. | 1. AI analyzes financial data.2. Recommendations are displayed clearly.3. Access depends on the subscription plan. | High
US-008 | Financial Calculators | As a user, I want access to financial calculators so that I can estimate savings, investments, and loan repayments. | 1. User can select a calculator.2. Inputs are validated.3. Results are calculated accurately. | Medium
US-009 | Advisor Consultation | As a user, I want to find a suitable financial advisor so that I can receive professional financial guidance. | 1. User submits their financial concern.2. System recommends relevant advisors.3. User can view advisor profiles. | High
US-010 | Advisor Consultation | As a user, I want to book an online consultation so that I can discuss my financial concerns with an advisor. | 1. User selects a date and time.2. Payment is completed successfully.3. Booking confirmation is generated. | High
US-011 | Subscription | As a user, I want to upgrade my subscription so that I can access premium features. | 1. Available plans are displayed.2. Payment is processed successfully.3. Premium features are unlocked immediately. | High
US-012 | Notifications | As a user, I want to receive reminders so that I do not miss budget updates, financial goals, or consultations. | 1. Notifications are generated based on events.2. User receives reminders at the appropriate time. | Medium

## Sprint Planning
Sprint | Duration | Sprint Goal | Backlog Items | Deliverables | Story Points | Status
Sprint 1 | 2 Weeks | Build the core application foundation and user authentication. | PB-001, PB-002, PB-003, PB-004 | User Registration, Login, Forgot Password, Dashboard | 19 | Planned
Sprint 2 | 2 Weeks | Enable users to manage their daily finances. | PB-005, PB-006, PB-007 | Expense Management, Expense History, Budget Planning | 18 | Planned
Sprint 3 | 2 Weeks | Introduce financial planning and AI-powered insights. | PB-008, PB-009, PB-010 | Goal Management, AI Insights, Financial Calculators | 26 | Planned
Sprint 4 | 2 Weeks | Complete premium features and advisor consultation services. | PB-011, PB-012, PB-013, PB-014, PB-015 | Advisor Matching, Consultation Booking, Video Consultation, Subscription Management, Notifications | 39 | Planned