## Sheet1
Stakeholder | Power | Interest | Category | Engagement Strategy
CEO / Founder | High | High | Manage Closely | Weekly meetings, project updates, key decisions
Product Manager | High | High | Manage Closely | Requirement discussions, sprint planning
Business Analyst | Medium | High | Manage Closely | Coordinate with all stakeholders
Development Team | Medium | High | Keep Informed | Daily stand-ups, requirement clarification
QA Team | Medium | Medium | Keep Informed | Testing updates, defect discussions
UI/UX Designer | Medium | High | Keep Informed | Design reviews, wireframe discussions
End Users | Low | High | Keep Informed | Surveys, feedback sessions, UAT
Financial Advisors | Low | High | Keep Informed | Consultation scheduling, platform updates
Customer Support | Low | Medium | Monitor | Product documentation and issue tracking
Marketing Team | Medium | Medium | Keep Satisfied | Feature updates before launch
Finance Team | Medium | Medium | Keep Satisfied | Billing and subscription updates
Legal & Compliance | High | Low | Keep Satisfied | Compliance reviews before release